## WBS-Template
Work Breakdown Structure Table
Provide basic information about the project including: Project Title – The proper name used to identify this project; Project Working Title - The working name or acronym that will be used for the project; Project Manager - the person with responsibility for the successful delivery of the project to time cost and quality. Project Sponor - the person ultimately accountable for the success of the project. Prepared by – The person(s) preparing this document; Date/Control Number – The date the plan is finalized and the change or configuration item control number assigned.
Project Title: |  |  |  | Project Working Title:
Project Manager: |  |  |  | Project Sponsor:
Prepared by: |  |  |  | Date / Control Number:
For more tips on completing this template see WBS Excel template
Element Number | WBS Elements Activity, Task, or Sub-Task Name | Estimed Time | Definition of Activity or Task (Description) | Responsible Person or Group | Estimated (E) or Actual (A) Cost (Cross reference to budget) | Project Phase (Cross reference to schedule)
The unique reference ID for the activity or task. | Enter the name or title of the Task, Sub-task, Activity or Deliverable. | 44 | Provide a brief description of this Activity, Task or Sub-Task. | Enter the person or group who are responsible | Enter the estimate or actual cost of the activity or task or add a cross reference to the budget. | Provide the name or number of the Project phase that this activity falls into.
1 | Auxl/Clientes/Grid sencillos - falta crud | 3 |  | Jordi
2 | Auxl-Clientes/Cargo presuppuesto | 0.3 |  | Jordi
3 | Estudiar data grid extension (dataset) | 2
4 | Estudiar convert para minimizar usercontrols (plantilla sensilla) | 2
5 | Estudiar de sobra la lupa en la form | 1
6 | Estudiar la WPF data grid extended y extenderla | 1
7 | Estudiar Region/Shell/ViewLocator | 2
8 | Esturdiar ERP/CRM OpenSourceWPF | 2
9 | Auxl/Clientes/Forma de Cobro | 3
10 | Aux/Clientes/Forma Sencillas1 | 3
11 | Aux/Clientes/Forma Sencillas2 | 3
12 | Aux/Clientes/Pais | 0.5
13 | Aux/Clientes/Poblaciones y Provincias | 1
14 | Aux/Clientes/Vendedores | 1
15 | Aux/Vehiculos/Extra | 1
16 | Aux/Vehiculos/Grupo Vehiculos | 6
17 | Aux/Vehiculos/CodigoMantenimiento | 1
18 | Aux/Vehiculos/Marcas | 2
19 | Aux/Vehiculos/Modelos | 2
20 | Aux/Vehiculos/Propietarios | 1
21 | Aux/Comisionista/EmpleadoAgencia | 0.2
22 | Aux/Tarifas/Conceptos de Facturacion | 1
23 | Aux/Texto estandards | 2
24 | Aux/Tipo Documentos | 1
25 | DAL | 2
26 | Screenshot | 1